## Sheet1
Due Date | Time (h) | Task | Comments
2019-04-08 | 3 | Vehicle/VehicleType Creation. |  | *All class-related tasks assume full implementation of tests and documentation
2019-04-10 | 1.5 | Burndown Creation |  | **Burndown will be updated as time requirements are realized
2019-04-10 | 0.5 | Employee Class | Currently just getters/setters to act as a superclass
2019-04-11 | 3 | Employee Management Class | The employee "Bag", data structure TBD
2019-04-13 | 5 | Garage/Space Classes | Need to decide on how to implement space distance
2019-04-15 | 3 | Ticket/Receipt Classes | Receipt just inherits Ticket
2019-04-17 | 3 | Attendant Class | Required for Manager to create it
2019-04-19 | 3 | Manager Class | All required classes should now be created
4/20-4/21 | 10 | Android Studio Study | Need to learn how to create the UI desired
2019-04-24 | 3 | Initial design created | Either in the form of notes, or a barebones Studio version
2019-04-02 | 15 | Backend linked to frontend | It is difficult to judge the time required for something you don't currently know. Update once time requirements are better known.
This task will involve the creation of controller classes and UI interactions.
2019-05-16 |  | Project Due | \-----COMPLETE-----/
Total Time | 50
Time Values
47
45.5
45
42
37
34
31
28
18
15
0